## Summary
| Priority | Initial Estimate | Actual Time Spent | Work Hours Left | Progress
Project 1 | High | 60 | 74 | 0 | 63.33%
Project 2 | Medium | 7 | 7 | 7 | 0%
Project 3 | Medium | 4.5 | 4.5 | 4.5 | 0%
Project 4 | Low | 9 | 9 | 9 | 0%
Extra Mile | Low | 12 | 12 | 12 | 0%
Total |  | 80.5 | 94.5 | 20.5 | 78.31%
Total (+ Extra) |  | 92.5 | 106.5 | 32.5 | 69.48%
Timeframe
Start Date | Deadline | Work Days Left | Weekend Days Left | Total Days Left
2023-01-17 | 2023-05-01 | 10.7143 | 4.0787 | 14.793
Statistics
Estimated Velocity | Actual Velocity | Velocity needed for deadline | Current Velocity
0.9 h/day | 1 h/day | 2.2 h/day | 0.8 h/day
Formulas:
Initial Estimate = MAX(0,([Priority]-TODAY()+1)/7*5)

## Project 1
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Section 1 | 2 | 2 | 0 | Done
Section 2 | 2 | 2 | 0 | Done
Section 3 | 2 | 2 |  | Done
Section 4 | 2 | 2 |  | Done
Section 5 | 2 | 2 |  | Done
Section 6 | 2 | 4 |  | Done
Section 7 | 2 | 2 |  | Done
Section 8 | 2 | 3 |  | Done
Section 9 | 2 | 5 |  | Done
Section 10 | 2 | 5 |  | Done
Section 11 | 2 | 5 |  | Done
Section 12 | 2 | 5 |  | Done
Section 13 | 2 | 5 |  | Done
Section 14 | 2 | 5 |  | Done
Section 15 | 2 | 5 |  | Done
Section 16 | 2 | 5 |  | Done
Section 17 | 2 | 5 |  | Done
Section 18 | 2 | 5 |  | Done
Section 19 | 2 | 5 |  | Done
Section 20 | 2 |  |  | Not Started
Section 21 | 2 |  |  | Not Started
Section 22 | 2 |  |  | Not Started
Section 23 | 2 |  |  | Not Started
Section 24 | 2 |  |  | Not Started
Section 25 | 2 |  |  | Not Started
Section 26 | 2 |  |  | Not Started
Section 27 | 2 |  |  | Not Started
Section 28 | 2 |  |  | Not Started
Section 29 | 2 |  |  | Not Started
Section 30 | 2 |  |  | Not Started

## Project 2
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 | 1 | 1 | Not Started
Task 4 | 1 | 1 | 1 | Not Started
Task 5 | 1 | 1 | 1 | Not Started
Task 6 | 1 | 1 | 1 | Not Started
Task 7 | 1 | 1 | 1 | Not Started

## Project 3
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 0.5 | 0.5 | 0.5 | Not Started
Task 2 | 0.5 | 0.5 | 0.5 | Not Started
Task 3 | 0.5 | 0.5 | 0.5 | Not Started
Task 4 | 0.5 | 0.5 | 0.5 | Not Started
Task 5 | 0.5 | 0.5 | 0.5 | Not Started
Task 6 | 1 | 1 | 1 | Not Started
Task 7 | 1 | 1 | 1 | Not Started

## Project 4
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 3 | 3 | 3 | Not Started
Task 2 | 3 | 3 | 3 | Not Started
Task 3 | 3 | 3 | 3 | Not Started

## Extra Mile
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 2 | 2 | 2 | Not Started
Task 2 | 2 | 2 | 2 | Not Started
Task 3 | 2 | 2 | 2 | Not Started
Task 4 | 2 | 2 | 2 | Not Started
Task 5 | 2 | 2 | 2 | Not Started
Task 6 | 2 | 2 | 2 | Not Started

## Gotchas
When you duplicate a tab, all named ranges will automatically be duplicated as well with name SHEET!ORIGINAL_NAME. In most cases, this is fine and there is nothing explicit you should change in that sheet. What you have to update, though, is the project row in the "Summary" sheet. Use some of the others as reference what to put there.
Renaming a sheet will not break your statistics in the "Summary " sheet.
There is a hidden column D in all your project tabs. It contains some numbers which are used to calcuate remaining and current velocity. Make sure the formulas in those columns are not broken, otherwise your stats will be incorrect.